## Sheet1
FEATURE | USER STORY | PRIORITY | STORY POINTS | RELEASE | ACCEPTANCE | DEPENDENCIES | REQUESTOR | NOTES | VALUE/RISK MATRIX | PRIORITY(INT) | VALUE(INT) | RISK(INT) | PRIORITY(INV) | VALUE(INV) | RISK(INV) | THEME(Sp) | FEATURE(Sp) | RELEASE(S) | ROW(S)
M.0.0.1 Create an Account | As a Customer, I want multiple ways to sign into my account | 1 High | 8 | MVP | 1. Multi sign on works 2. Backend keep records all users and their multi sign-on credential | None | PM
M.0.0.2 Create an Account | As a Customer, I want a favourite list for all my items for easy checkout | 1 High | 3 | MVP | 1. Backend create a list 2. Backend keeps persistent all recurrent activity of all user | None | PM
M.0.0.3 Create an Account | As a Sale manager, I want Customer account creation to be multi sign on, and a dashboard displaying customer performance . | 1 High | 13 | MVP | 1. Multi sign on works 2. Backend keeps persistent record all users and their previous sign-on activity 3. Backend to create a table displaying user performance 4. Sales has ways to query and receive updates on performance | M.0.0.1 | Eng